CSIT214/CSCI814/HCSC814 IT Project Management

Lab – Week 3

- Make sure you have had a group for the project and your group has registered using the link on Moodle by the end of this week.  If you haven’t got a group, use the forum setup on Moodle to find people to form a group with you.  Try to form a group of people with mixed skillsets (e.g. programming, analysis, design, documentation, etc.)

- If you haven’t done it, follow the instructions below to download and install Microsoft Project on your PC/laptop:

- Go to the link https://azureforeducation.microsoft.com/devtools

- Login with your UOW email account

- Click to “Software” link on the left (under “Learning resources”)

  - Search for Project (either 2016 or 2019 version is fine) and follow the instructions to install it.

If your computer is not a Windows machine, you can install a virtual machine and then install a Windows OS on it (the list of software in the Azure for Education link above also includes Windows). See this link https://www.howtogeek.com/657464/how-to-install-a-windows-10-virtualbox-vm-on-macos/ for an example.

- Using MS Project to complete the following tasks:

You are given the following tasks for a project.

| Task ID | Description | Duration (days) | Predecessor task |
| --- | --- | --- | --- |
| 1 | Develop Business Plan | 2 days |  |
| 2 | Develop Project Charter | 1 day | 1 |
| 3 | Sign Project Charter | 1 day | 2 |
| 4 | Develop strategic plan of software | 5 days | 3 |
| 5 | Develop strategic plan of hardware | 3 days | 3 |
| 6 | Review strategic plans and determine if appropriate | 5 days | 4,5 |
| 7 | Get senior management to approve strategic plan | 1 day | 6 |
| 8 | Develop communication plan for strategic plan | 7 days | 7 |
| 9 | Communicate approved strategic plan and documentation in printed and software format | 10 days | 8 |
| 10 | Create software system | 10 days | 9 |
| 11 | Install hardware components | 5 days | 9 |
| 12 | Review software system | 3 days | 10 |
| 13 | Review hardware installations | 3 days | 11 |
| 14 | Prepare lessons learnt report | 2 days | 12,13 |
| 15 | Close project | 2 days | 14 |

Enter the above tasks, duration and predecessor task to Microsoft Project. Ensure all tasks are auto scheduled. Please save this project plan for future labs.

Answer the following questions:

1. Explore the Network Diagram and Calendar views.

2. List the tasks that are in the critical path. What does the critical path tell you?

3. When will this project complete?

4. Based on your project plan, when will you begin to install hardware components?

5. If the duration for task “Develop communication plan for strategic plan” were to change to 20 days, how would it affect your project completion date?

6. It has taken 4 days to implement the task, “develop strategic plan of hardware”, will it affect the start date for the task “Review strategic plans and determine if appropriate”? Explain your answer.

7. You have identified three phases for this project: Initiation (tasks 1 to 3), Planning (tasks 4 to 8), implementation (tasks 9 to 13) and closing (task 14 to 15). Add these phases as summary task to your project plan.

8. Include four milestones to your project plan at the end of each phase.

9. Include a Project Summary Task to your project plan.

10. Format the Gantt chart so that task name appears on the bottom of the task bar.

11. Revise your project plan by considering any the Australian public holidays in NSW, what is your new project completion date?

12. The company decides to change the working hours to 35 hours per week (i.e. the working hours are 8.30am-12.30pm and 1.30pm -4.30pm), revise your project plan to include these changes. What is the new project completion date?

13. You have scheduled the project using the “Project Start Date”, when should the project starts be if you were to schedule the project using “Project Finish Date” and the project must complete on 20/09/2020.

Optional task:

Create a project consisting of 10 tasks (your project must be meaningful, i.e. the task description and duration must also be meaningful).

Your project plan must show evidence of the following:

1. Gantt chart with task name appears inside the task bar.

2. Project Summary Task and appropriate summary tasks.

3. Appropriate milestones.

4. Ensure that the working hours are Monday to Friday 9.00am-12.30pm and 1.30pm - 5.30pm and appropriate public holidays are included in your project plan.