CSIT214/CSCI814/HCSC814 IT Project Management

Lab – Week 4

Task 1: (Verbal progress report for the project) – 3 minutes per group

- One member from each group presents the progress of their group

  - Use 1-2 slides

  - Introduce their group members and their roles.

  - Report on progress and plans for the remaining of the project.

Task 2:

Create a precedence activity network using the following details. You can draw this on paper or use a tool of your choice.

| Activity | Depends on | Duration (days) |
| --- | --- | --- |
| A |  | 5 |
| B | A | 7 |
| C | B | 6 |
| D | A | 5 |
| E | D | 10 |
| F | B | 15 |
| G | B | 8 |
| H | G | 8 |
| I | C | 4 |
| J | G | 4 |
| K | E,F | 5 |
| L | I,H | 3 |

Calculate the earliest and latest start and end dates and the float associated with each activity. From this identify the critical path.