CSIT214/CSCI814/HCSC814 IT Project Management

Lab – Week 10

Task 1:

Consider the following activity network and the PERT activity time estimates for each activity. Activity durations are in weeks.

| Task | a | m | b | te | s |
| --- | --- | --- | --- | --- | --- |
| A | 5 | 6 | 8 |  |  |
| B | 3 | 4 | 5 |  |  |
| C | 2 | 3 | 3 |  |  |
| D | 3.5 | 4 | 5 |  |  |
| E | 1 | 3 | 4 |  |  |
| F | 8 | 10 | 15 |  |  |
| G | 2 | 3 | 4 |  |  |
| H | 2 | 2 | 2.5 |  |  |

- Calculate the expected time (te) and standard deviation (s) for each activity.

- Calculate the expected time and the z value for the project completion.

- What is the chance of not meeting the target date of the end of week 12?

Task 2: Below are details of a project. All times are in days

| Activity | Depends on | Most likely | Plus safety/comfort zone |
| --- | --- | --- | --- |
| A |  | 10 | 14 |
| B | A | 5 | 7 |
| C | B | 15 | 21 |
| D | A | 3 | 5 |
| E | A | 8 | 12 |
| F | E | 20 | 22 |
| G | D | 6 | 8 |
| H | C,F,G | 10 | 14 |

Draw up an activity diagram applying critical chain principles for this project

- Locate the places where buffers will need to be located

- Assess the size of the buffers

- Start all activities as late as possible