CSIT214/CSCI814/HCSC814 IT Project Management

Week 11

This exercise is focusing on how to view and report project status.

- Visit the following Web sites for a quick tutorial on status reporting.  https://www.tutorialspoint.com/ms_project/ms_project_status_reporting.htm

- If you purchased the reference book MS Project 2016 Step by Step, refer to Chapters 15 and 17 for details.

Some functions you will use:

  - To open the Project Statistics dialog box, click the File tab to display the Backstage view, and then click the Info tab. On the Info page, click Project Information and then click Project Statistics.

  - To display a Dashboard report (including Project Overview, Cost Overview, and Burndown reports), on the Report tab, in the View Reports group, click Dashboards, and then click the Dashboard report you want.

  - To display the Variance table the Task Sheet view, on the View tab, in the Task Views group, click Other Views, and then click Task Sheet to display the Task Sheet view. On the View tab, in the Data group, click Tables -> Variance.

  - To display the Tracking Gantt view, on the View tab, in the Task Views group, click the Gantt Chart arrow, and then click Tracking Gantt.

  - To display the Late Tasks or Slipping Tasks report, on the Report tab, in the View Reports group, click In Progress, and then click the report you want.

  - To display the Cost table in the Task Sheet view, on the View tab, click Other Views, and then click Task Sheet. On the View tab, click Tables->Cost.

  - To display the Task Cost Overview or Cash Flow report, on the report tab, in the View Reports group, click Costs, and then click the report you want.

  - To display the Budget Cost visual report, on the Report tab, in the Export group, click Visual Reports to open the Visual Reports dialog box. Click the Assignment Usage tab, click Budget Cost Report, and then click View. The report appears in Excel.

  - To display the Cost table in the Resource Sheet view, on the View tab, click Resource Sheet. On the View tab, click Tables->Cost.

  - To sort resources by cost amounts, display the Cost table, click the AutoFilter arrow in a column heading such as Cost or Variance, and in the menu that appears, click Sort Largest to Smallest.

  - To display the Cost table and cost details in the Resource Usage view, on the View tab, click Resource Usage. On the View tab, click Tables->Cost. On the Resource Usage Tools Format tab, in the Details group, click the Cost detail to add it to the timephased side of the view. To add more timephased details, click Add Details to open the detail styles dialog box, then in the Available Fields list, click the fields you want to add, and click Show.

  - To display the Resource Cost Overview report, on the Report tab, click Costs, and then click Resource Cost Overview.

  - To create a new report, on the Report tab, in the View Reports group, click New Report. To add a chart/table/text box/shape/image to a report, on the Report Tools Design tab, in the Insert group, click chart/table/text box/shape/image. Then drag the chart/table/text box/shape/image to position it where you want it on the report.

  - To select the project information to include in a chart, select the chart, in the Field List pane, click the type of data you want to work with. Select appropriate values in the Select Category list and in the Select Fields box. At the bottom of the Field List pane, select any filter or other options you want to apply to the tasks or resources. To change a chart’s format and style, select options on the Chart Tools Format tab and Chart Tools Design tab.

  - To select the project information to include in a table, select the table, in the Field List pane, click the type of data you want to work with. Select appropriate values in the Select Fields box. To change a table format and style, select options on the Table Tools Format tab and Table Tools Design tab.

- Download and open ReportStatus from Moodle and complete the following.

- Locate the plan’s overall schedule variance of its finish date in the Project Statistics dialog box.

- Display the Project Overview report, and note the percent complete values of the top-level summary tasks.

- Display the Variance table in the task Sheet view.

- Filter the table to display only summary tasks.

- Identify the summary tasks of the plan that have incurred the highest finish variance.

- Display the Slipping Tasks report, and identify the tasks with the most remaining work that have slipped from the baseline.

- Display the Cost table in the Task Sheet view to find the total remaining costs per summary task.

- Display the Task Cost Overview report, and then find the expected cost of the plan’s incomplete future tasks.

- Display the Cost table in the Resource Sheet view.

- Sort the resources from most to least cost variance.

- Download and open FormatReportsInDepth from Moodle and complete the following.

- Create a new blank report.

- Name the custom report Gourmet Cookbook Cost Summary.

- Insert a pie chart. Use the default two-dimensional pie chart style.

- Insert a table and position it below the pie chart

- Update the information in the Field List pane of the pie chart so the chart includes only the cost field and not the work field.

- Set the Filter value to All tasks, the group by value to no group, and the outline level value to level 1.

- Apply the style 3 style.

- Update the information in the Field list pane of the table to show the Resource field names.

- Leave the name field selected, but remove the Start and Finish date fields.

- In the Cost field group, select the Actual Cost, Remaining Cost, and Cost fields.

- Apply the Medium Style 2 – Accent 2 style.